## Tanisha
Agile Task Board
Assigned To: | Tanisha Singh
Use Case: | Use Case 1
Team: | Team C
Task | No. of Hours Expected | Actual No. of Hours
Raw Material Inventory
Create SQL Server table named "RawMaterialInventory" | 0.5 | 1
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create Raw Material Service using Angular for CRUD operations | 2 | 2 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Raw Material Inventory Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Raw Material Inventory Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Raw Material Inventory Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Raw Material Page" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
Raw Material Order Details
Create SQL Server table named "RawMaterialOrderDetails" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create Order Details Service using Angular for CRUD operations | 1 | 1 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Raw Material Order Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Raw Material Order Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Raw Material Order Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Raw Materials Order Details Page" using Bootstrap & Angular | 1 | 1
Task | Actual No. of Hours Expected | Actual No. of Hours
Raw Material Order
Create SQL Server table named "RawMaterialOrder" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create Orders Service using Angular for CRUD operations | 1 | 1 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Raw Material Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Raw Material Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Raw Material Orders Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Raw Material Order Page" using Bootstrap & Angular | 1 | 1

## Sagar
Agile Task Board
Assigned To: | Sagar Sharma
Use Case: | Use Case 2
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Products Inventory
Create SQL Server table named "ProductInventory" | 0.5 | 1
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create Product Service using Angular for CRUD operations | 2 | 3 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Products Inventory Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Create Products Inventory Page" using Bootstrap & Angular | 3 | 4
UI - Create Angular Component & Template for "Edit Products Inventory Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Products Page" using Bootstrap & Angular | 2 | 3
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Products Order Details
Create SQL Server table named "ProductOrderDetails" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create Order Details Service using Angular for CRUD operations | 1 | 1
UI - Create Angular Component & Template for "Products Order Details Page" using Bootstrap & Angular | 2 | 2 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Create Products Order Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Products Order Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Productss Order Details Page" using Bootstrap & Angular | 1 | 1.5

## Astha
Agile Task Board
Assigned To: | Astha
Use Case: | Use Case 1
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Supplier Details
Create SQL Server table named "Supplier Details" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create Supplier Details Service using Angular for CRUD operations | 2 | 2.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Supplier Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Supplier Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Supplier Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Supplier Details Page" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Supplier Address
Create SQL Server table named "Supplier Address" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create Supplier Address Service using Angular for CRUD operations | 1 | 1 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Supplier Address Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Supplier Address Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Supplier Address Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Supplier Address Page" using Bootstrap & Angular | 1 | 1

## Pulak
Agile Task Board
Assigned To: | Pulak
Use Case: | Use Case 1
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Distributor Details
Create SQL Server table named "Distributor Details" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create Distributor Details Service using Angular for CRUD operations | 2 | 2 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Distributor Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Distributor Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor Details Page" using Bootstrap & Angular | 1 | 1.5
Assigned To: | Pulak
Use Case: | Use Case 2
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Distributor Address
Create SQL Server table named "Distributor Address" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create Distributor Address Service using Angular for CRUD operations | 1 | 1 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Address Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Distributor Address Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Distributor Address Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor Address Page" using Bootstrap & Angular | 1 | 1

## Shivam
Agile Task Board
Assigned To: | Shivam
Use Case: | Use Case 1
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Raw Material Transaction Details
Create SQL Server table named "Raw Material Transaction Details" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 2
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create Raw Material Transaction Details Service using Angular for CRUD operations | 2 | 2.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Raw Material Transaction Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Raw Material Transaction Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Raw Material Transaction Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Raw Material Transaction Details Page" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Product Transaction Details
Create SQL Server table named "Product Transaction Details" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create Product Transaction Details Service using Angular for CRUD operations | 1 | 1.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Product Transaction Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Product Transaction Details Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Product Transaction Details Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Product Transaction Details Page" using Bootstrap & Angular | 1 | 1