## Shobit
Agile Task Board
Assigned To: | Shobhit Pitale
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Admin
Create SQL Server table named "Admin" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create AdminService using Angular for CRUD operations | 2 | 2 | mistakes with letter casing
UI- Create Angular Component & Template for "Admin Login Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Admin Page" using Bootstrap & Angular | 1.5 | 1.5
UI - Create Angular Component & Template for "Create Employee Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Edit Employee Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Change Admin Password" using Bootstrap & Angular | 1 | 2

## Siddhart
Agile Task Board
Assigned To: | Siddharth R Taklikar
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Loan
Create SQL Server table named "Loans" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations and other functionalities | 2 | 3
Prepare Test Cases using Excel MSUnit for all CRUD operations and other functionalities | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations and other functionalities | 2 | 2.5
UI - Create LoansServices using Angular for CRUD operations and other functionalities | 2 | 3 | issues with array and object
UI - Create Angular Component & Template for "Loan Services" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Apply for Loan Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Update Loan" using Bootstrap & Angular | 2.5 | 3
UI - Create Angular Component & Template for "Delete Loan" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Show Loan" using Bootstrap & Angular | 1 | 1.5

## Ashmita
Agile Task Board
Assigned To: | Asmita Chandrakar
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Customer
Create SQL Server table named "Customer" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issue with routing
UI - Create CustomerService using Angular for CRUD operations | 2 | 3
UI - Create Angular Component & Template for "Customers Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Add Customer Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Update Customer Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Search Customer Page" using Bootstrap & Angular | 1 | 2

## Akash
Agile Task Board
Assigned To: | Akash Singh
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Regular Account
Create SQL Server table named "RegularAccount" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create AccountsService using Angular for CRUD operations | 2 | 2.5 | issue with concept and mistakes in character casing
UI - Create Angular Component & Template for "Create Regular Account Page for existing Customer" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Create Regular Account Page for new Customer" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Update/Modify Regular Account" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Regular Account Page" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Search Regular Account Page" using Bootstrap & Angular | 2 | 2.5
Task | Actual No. of Hours Expected | Actual No. of Hours
Fixed Account
Create SQL Server table named "FixedAccount" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create AccountsService using Angular for CRUD operations | 1 | 1 | issue with concept and mistakes in character casing
UI - Create Angular Component & Template for "Create Fixed Account Page for existing Customer" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Fixed Account Page for new Customer" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Update/Modify Fixed Account" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Fixed Account Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Search Fixed Account Page" using Bootstrap & Angular | 1 | 1

## Tarunsree
Agile Task Board
Assigned To: | Tarunsree
Use Case: | Use Case
Team: | Team E
Task | Actual No. of Hours Expected | Actual No. of Hours
Debit Card
Create SQL Server table named "DebitCard" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create UtilitiesService using Angular for CRUD operations | 2 | 2 | issue with concept and mistakes in character casing
UI - Create Angular Component & Template for "DebitCard" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Add DebitCard Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Update DebitCard Status Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Search DebitCard" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Display List Of Debit Cards" using Bootstrap & Angular | 2 | 2.5
Task | Actual No. of Hours Expected | Actual No. of Hours
Credit Card
Create SQL Server table named "CreditCard" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create UtilitiesService using Angular for CRUD operations | 1 | 1 | issue with concept and mistakes in character casing
UI - Create Angular Component & Template for "CredtCard" using Bootstrap & Angular | 1 | 1
UI - Create Angular Component & Template for "Add CreditCard Page" using Bootstrap & Angular | 1 | 1
UI - Create Angular Component & Template for "Update CreditCard Status Page" using Bootstrap & Angular | 1 | 2
UI - Create Angular Component & Template for "Search CreditCard Based On CustomerIdPage" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Display List Of All Credit Cards" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
Cheque Book
Create SQL Server table named "ChequeBook" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create UtilitiesService using Angular for CRUD operations | 2 | 2
UI - Create Angular Component & Template for "ChequeBook" using Bootstrap & Angular | 2 | 2 | issue with concept and mistakes in character casing
UI-Create Angular Component & Template for "Add ChequeBook Page" using Bootstrap & Angular | 3 | 3
UI - Create Angular Component & Template for "Update ChequeBook Status Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Search ChequeBook Based On AccountId" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Display List Of All Cheque Books" using Bootstrap & Angular | 2 | 2