## Sowrasree
Agile Task Board
Assigned To: | Sowrasree Banerje
Use Case: | Use Case 3
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
Distributor
Create SQL Server table named "Distributor" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create Distributor using Angular for CRUD operations | 2 | 2 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Distributor Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update Distributor" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
DistributorAddress
Create SQL Server table named "DistributorAddress" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create DistributorAddress using Angular for CRUD operations | 1 | 1.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Distributor" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor" using Bootstrap & Angular | 1 | 1

## Rohit
Agile Task Board
Assigned To: | Rohit Kumar
Use Case: | Use Case 2
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
Distributor
Create SQL Server table named "RawMaterial" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array and routing
UI - Create Distributor using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Rawmaterial Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add RawMaterial" Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update RawMaterial" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete RawMaterial" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
DistributorAddress
Create SQL Server table named "Product" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create DistributorAddress using Angular for CRUD operations | 1 | 1 | issues with array and routing
UI - Create Angular Component & Template for "Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Product Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Product page" using Bootstrap & Angular | 1 | 1.5

## Maski
Agile Task Board
Agile Task Board | Maski Saijahnavi
Use Case: | Use Case 3
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
ProductOrder
Create SQL Server table named "ProductOrders" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array and routing
UI - Create OrdersService using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Product Orders Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Create Product Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
ProductOrderDetails
Create SQL Server table named "ProductOrderDetails" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2 | issues with array and routing
UI - Create OrdersService using Angular for CRUD operations | 1 | 1.5
UI - Create Angular Component & Template for "Product Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Product Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1

## Ritwik
Agile Task Board
Agile Task Board | Ritwik Sinha
Use Case: | Use Case 2
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
RawMaterialOrder
Create SQL Server table named "RawMaterialOrders" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2
UI - Create OrdersService using Angular for CRUD operations | 2 | 2.5 | issues with array and routing
UI - Create Angular Component & Template for "RawMaterial Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create RawMaterial Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
RawMaterialOrderDetails
Create SQL Server table named "RawMaterialOrderDetails" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2
UI - Create OrdersService using Angular for CRUD operations | 1 | 1 | issues with array and routing
UI - Create Angular Component & Template for "RawMaterial Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create RawMaterial Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1.5

## Pushpraj
Agile Task Board
Assigned To: | Pushpraj Kaushik
Use Case: | Use Case 1
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
Supplier
Create SQL Server table named "Supplier" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array, routing and character casing
UI - Create Supplier using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Supplier Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update Supplier" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Supplier" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
SupplierAddress
Create SQL Server table named "SupplierAddress" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2
UI - Create SupplierAddress using Angular for CRUD operations | 1 | 1 | issues with array, routing and character casing
UI - Create Angular Component & Template for "Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Supplier" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Supplier" using Bootstrap & Angular | 1 | 1.5