## Aishwarya
Agile Task Board
Assigned To: | Aishwarya Sarna
Use Case: | Use Case 1 and 2
Team: | Team F
Task | Actual No. of Hours Expected | Actual No. of Hours
Admin
Create SQL Server table named "Admins" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2 | issues with array, objects and character casing
UI - Create AdminsService using Angular for CRUD operations | 1 | 1.5
UI - Create Angular Component & Template for "Admin's Page" using Bootstrap & Angular | 1 | 1.5
UI - Create Angular Component & Template for "Create Admin Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Admin Page" using Bootstrap & Angular | 2 | 2.5
Employee
Create SQL Server table named "Employees" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel MSUnit for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array, objects and character casing
UI - Create Employee's Service using Angular for CRUD operations | 2 | 2
UI - Create Angular Component & Template for "Employee's Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Employee Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Employee Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Employee Page" using Bootstrap & Angular | 1 | 2

## Aditya
Agile Task Board
Assigned To: | Aditya Khatavkar
Use Case: | Use Case 1
Team: | Team F
Task | Actual No. of Hours Expected | Actual No. of Hours
Accounts
Create SQL Server table named "Accounts" and "FixedDeposit" | 1 | 1
Create Stored Procedures for all CRUD Operations | 3 | 3
Prepare Test Cases using Excel for all CRUD operations | 1.5 | 2
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create AccountsService using Angular for CRUD operations | 2 | 2.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Accounts Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Create Accounts Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Accounts Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Accounts Page" using Bootstrap & Angular | 1 | 2

## Ayush
Agile Task Board
Assigned To: | Ayush Soni
Use Case: | Use Case 1
Team: | Team F
Task | Number of Hours Expected | Actual No. of Hours
Transactions
Create SQL Server table named "Transactions" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 3
UI - Create TransactionsService using Angular for CRUD operations | 2 | 2.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Transactions Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Create Transaction Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Edit Transactions Page" using Bootstrap & Angular | 2 | 3
UI - Create Angular Component & Template for "Delete Transactions Page" using Bootstrap & Angular | 1 | 1.5