## Tanisha
Agile Task Board
Assigned To: | Tanisha Singh
Use Case: | Use Case 1
Team: | Team C
Use Case | Task | No. of Hours Expected | Actual No. of Hours
Raw Material Inventory
Create SQL Server table named "RawMaterialInventory"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Raw Material Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Raw Material Inventory Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Raw Material Inventory Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Raw Material Inventory Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Raw Material Page" using Bootstrap & Angular
Assigned To: | Tanisha Singh
Use Case: | Use Case 2
Team: | Team C
Use Case | Task | Actual No. of Hours Expected | Actual No. of Hours
Raw Material Order Details
Create SQL Server table named "RawMaterialOrderDetails"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Order Details Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Raw Material Order Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Raw Material Order Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Raw Material Order Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Raw Materials Order Details Page" using Bootstrap & Angular
Assigned To: | Tanisha Singh
Use Case: | Use Case 3
Team: | Team C
Use Case | Task | Actual No. of Hours Expected | Actual No. of Hours
Raw Material Order
Create SQL Server table named "RawMaterialOrder"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Orders Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Raw Material Orders Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Raw Material Orders Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Raw Material Orders Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Raw Material Order Page" using Bootstrap & Angular

## Sagar
Agile Task Board
Assigned To: | Sagar Sharma
Use Case: | Use Case 2
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Products Inventory
Create SQL Server table named "ProductInventory"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Product Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Products Inventory Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Products Inventory Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Products Inventory Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Products Page" using Bootstrap & Angular
Assigned To: | Tanisha Singh
Use Case: | Use Case 2
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Products Order Details
Create SQL Server table named "ProductOrderDetails"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Order Details Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Products Order Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Products Order Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Products Order Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Productss Order Details Page" using Bootstrap & Angular
Assigned To: | Tanisha Singh
Use Case: | Use Case 3
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Products Order
Create SQL Server table named "ProductOrder"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Orders Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Products Orders Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Products Orders Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Products Orders Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Products Order Page" using Bootstrap & Angular

## Astha
Agile Task Board
Assigned To: | Astha
Use Case: | Use Case 1
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Supplier Details
Create SQL Server table named "Supplier Details"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Supplier Details Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Supplier Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Supplier Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Supplier Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Supplier Details Page" using Bootstrap & Angular
Assigned To: | Astha
Use Case: | Use Case 2
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Supplier Address
Create SQL Server table named "Supplier Address"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Supplier Address Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Supplier Address Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Supplier Address Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Supplier Address Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Supplier Address Page" using Bootstrap & Angular

## Pulak
Agile Task Board
Assigned To: | Pulak
Use Case: | Use Case 1
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Distributor Details
Create SQL Server table named "Distributor Details"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Distributor Details Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Distributor Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Distributor Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Distributor Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Distributor Details Page" using Bootstrap & Angular
Assigned To: | Pulak
Use Case: | Use Case 2
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Distributor Address
Create SQL Server table named "Distributor Address"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Distributor Address Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Distributor Address Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Distributor Address Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Distributor Address Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Distributor Address Page" using Bootstrap & Angular

## Shivam
Agile Task Board
Assigned To: | Shivam
Use Case: | Use Case 1
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Raw Material Transaction Details
Create SQL Server table named "Raw Material Transaction Details"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Raw Material Transaction Details Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Raw Material Transaction Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Raw Material Transaction Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Raw Material Transaction Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Raw Material Transaction Details Page" using Bootstrap & Angular
Assigned To: | Shivam
Use Case: | Use Case 2
Team: | Team C
Task | Actual No. of Hours Expected | Actual No. of Hours
Create Product Transaction Details
Create SQL Server table named "Product Transaction Details"
Create Stored Procedures for all CRUD Operations
Prepare Test Cases using Excel MSUnit for all CRUD operations
Prepare Test Cases using MSUnit test cases for all CRUD operations
UI - Create Product Transaction Details Service using Angular for CRUD operations
UI - Create Angular Component & Template for "Product Transaction Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Create Product Transaction Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Edit Product Transaction Details Page" using Bootstrap & Angular
UI - Create Angular Component & Template for "Delete Product Transaction Details Page" using Bootstrap & Angular